## Slide 1
Sprint 3
Retrospective
Team B
Notes: *

## Slide 2: Outline
Sprint Productivity
Overall Productivity
Acceptance Test Reports
Process Review
Notes: *

## Slide 3: Sprint Task Completion
Integrate Algorithm with GUI, which involved moving C# code to Qt
Develop Degree Requirements 2-4 years
Develop Class Data
Create Detail User Diagram

## Slide 4: Sprint Productivity
Metric | Value
# of Use Cases Completed (sub/overall) | 3
# of Use Cases Planned (sub/overall) | 5
# of Story Points Completed | 6
# of Story Points Planned | 10
% of Story Points Completed | 60%
Hours of Effort this Sprint | 55
Hours of Testing this Sprint | 10
% of Effort Spent Testing this Sprint | 18%
Sprint Velocity (Story Points per Hour) = People x hours x days of work | .220
Notes: *

## Slide 5: Overall Productivity
Metric | Value
# of Use Cases Completed (sub/overall) | 15
# of Use Cases in Product (sub/overall) | 25
# of Story Points Completed | 16
# of Story Points in Product | 42
% of Story Points Completed | 38%
Hours of Effort to Date | 167
Hours of Testing to Date | 31
% of Effort Spent Testing to Date | 18.6%
Overall Velocity (Story Points per Hour) | .440
Notes: *

## Slide 6: Acceptance Test Report – UC002
Test # | Test Purpose | Test Result | Comment
002.1 | Main Flow - Valid 2 Year Schedule | PASS | Not including SQL integration
002.2 | Main Flow – Valid 2 Year Schedule with GUI and Algorithm Integration | PASS | Not including SQL integration
002.3 | Alt FLow - Invalid Schedule | FAIL | Unhandled
Notes: *

## Slide 7: Process Review
Stop
  Collecting data for POS
Continue
  Delegating tasks, working towards complete functionality
Start
  Meeting at regular defined intervals
  Checking files into repository
  Storyboarding
Notes: *